## UAT Observation
S.No | CUIC Report | AU_Observation | Servion Comments | Summary
1 | Agent productivity | Outcall call count mismatch | AU has to provide agent id and list of phone call details with timestamp made by agent,so that servion will analyse futher. Servion-31/07 : it is fixed, we will discuss if it is showing still discrepancies, based on system record with manual outbound made in excel sheet. | Fixed
|  | Please exclude other talk time in the calculation of " Average Talk time" | We have not included "other talk time" in "Average Talk time" Servion -31/07 - it is already not been added | Clarification given
2 | Not ready Refresh data | a.)Please add Agent id. | Fixed | Fixed
3 | Login/Logout Report | Required real time report. | It will be realtime report with 45 minutes delay. It is advisable not to generate frequently during high call volume | Clarification given
4 | Service Level Inbound Report | Skill group name has be removed | Fixed | Fixed
5 | Individual agent report to be made available on the CTI screen | Not working on Finesse since the day it was incorporated | Fixed | Fixed
6 | Data of abandoned calls to be provided on daily basis | Report has to be 24x7. its is showing data only from 7 AM to 11 PM. | it is already being geneated for 24*7. Call ended in IVR due to non-avaialability of agent will not be considered as abandonded hence call details are not available at the time when agents are not available Servion - 31/07 it is fixed, Sandhya has to confirm | Fixed
7 | Customer hung up/agent hung up identification report – Need the fields which you are looking for | Report is not available in Custom report. Attached CUIC screenshot. In supervisor id all the report is not coming. However in CUIC admin page all reports are coming. | Fixed | Fixed
8 | Short Call Report | Report is not available in Custom report. Attached CUIC screenshot. In supervisor id all the report is not coming. However in CUIC admin page all reports are coming. | Fixed Servion : 31/07 In short call report for some of calls in a day, duration showing more than 5 sec, We have raised Cisco TAC SR No is SR 682778216 | In-Progress
9 | Wrapupcodewsie_Report | showing data only from 1st to 5th July 2017. | As discussed, the detail report is generated for whole month, which is overlimiting the total CUIC grid limitation.To mitigate this, the new Monthly wise report has to be developed. For this development, effort has to be discussed Servion : 31/07 This has been clarified, this is due to Cisco platform we could not provide monthly detail report as number of rows are more than permitted one
|  | Also tried pulling data in for different dates (10th to 15th July & 17th to 21st July) but remain incorrect. |  | Clarification given
10 | Service_Level_Inbound_Report | There is a difference in call count for 18-7-17 CUIC report, Reports pulled of Custom reports also depict the same error of different figures. | Customer compared "Agent_Skill_Group_Historical_All_Fields" with "Service_Level_Inbound_Report" 1. Total handled in Agent_Skill_Group_Historical should be equalant to calls answered in "Service_Level_Inbound_report" 2. Calls offered and Total Handled will not be same, Since Calls-offered in Service level report will include Abandoned calls in queue. Servion : 31/07 above clarificaiton is given | Clarification given
|  | Please clarify in Inbound Call Dump and Daily Abandon Report is showing with similar count whereas in Service Level Inbound Report is showing with different number. | InProgress | In-Progress
11 | Daily_abandond_report | Please explain the difference between Abandoned in Network and Abandoned in Agent Network.
|  | Abandond in Network | In Unified ICM, indicates the call was abandoned, or dropped, before being terminated at a target device (for instance, an ACD, IVR, Desklink, etc.). | Clarification given
|  | Abandoned Agent Terminal | In Unified ICM, indicates the call was dropped while being held at an agent device. For example, the caller is connected to an agent; the agent puts the caller on hold; the caller gets tired of waiting and hangs up Servion 31/07 Based on today confirmation from Sandhya "Abandoned AgentTerminal" count has been removed | Fixed
12 | Not ready Report | System Failure | A CTI component failed, causing the agent to be logged out. This could be due to closing the agent desktop application, heartbeat time out, a CTI Server failure | Clarification given
13 | Agent productivity | In APR report complete summery is not coming | Servion 31/07 : As discussed OverAll Average of Each agent's Average has been given | Fixed
14 | Agent productivity | Outcall Mismatch | Servion 31/07 : This has been fixed, Sandhya has to confirm from their business team whether their actual dial count is matching with System count | Fixed